## RAID
Project Atlas (PRJ-3101) - RAID log
Updated 2 Oct 2026 (W40). Score = probability x impact (1-5 each).
Classification: Confidential
ID | Type | Description | Probability | Impact | Score | Status | Owner | Mitigation / action | Due
R-014 | Risk | Wave 2 POS instability continues into holiday peak (from 23 Nov) | 4 | 5 | 20 | Open | Arjun Mehta | Stabilisation squad; daily store-ops call; change freeze from 16 Nov | 2026-10-30
R-019 | Risk | Loyalty de-duplication corrupts points balances | 2 | 5 | 10 | Open | Kavya Iyer | Dry run on copy of production; reconciliation of 11.2M balances before and after | 2026-10-13
R-021 | Risk | AMS renewal lost because of Atlas performance | 3 | 5 | 15 | Open | Priya Raman | Recovery plan 8 Oct; executive sponsorship (Laura Chen) | 2027-01-15
R-022 | Risk | Fixed-price overrun beyond revised EAC ($3.96M) | 3 | 4 | 12 | Open | Kavya Iyer | Weekly EAC review with Finance; change request for wave 3 scope | 2026-12-15
I-031 | Issue | INC-48211: 14 wave 2 stores lost POS on 26 Sep (loyalty lookup timeout blocked tender) | 5 | 5 | 25 | Mitigated | Arjun Mehta | Circuit breaker deployed 30 Sep; offline fallback in all 212 stores | 2026-09-30
I-033 | Issue | 2.3% duplicate loyalty member IDs (~258K records) from migration | 5 | 4 | 20 | In progress | Kavya Iyer | De-dup job in test; production 13 Oct | 2026-10-13
I-034 | Issue | Client sponsor (Daniel Okafor) exited 28 Sep | 5 | 4 | 20 | Open | Priya Raman | Build relationship with Sofia Lindqvist (VP Technology from 1 Oct) | 2026-10-16
A-007 | Assumption | Northwind store IT completes network readiness 2 weeks before each wave | 3 | 3 | 9 | Open | Mark Ellison | Readiness checklist per store | 2027-01-08
D-005 | Dependency | Northwind CFO approval for wave 3 change request (OPP-24103) | 4 | 3 | 12 | Blocked | Priya Raman | CFO spend freeze until January | 2027-01-15
D-006 | Dependency | POS hardware vendor delivers 1,760 terminals for wave 3 | 2 | 4 | 8 | Open | Northwind Procurement | Delivery confirmed for 12 Jan 2027 | 2027-01-12