## Projects
Strategic programmes and projects - status at week 40 (2 Oct 2026)
Cost figures are delivery cost (USD). Projected margin = (contract - EAC) / contract.
Classification: Confidential
Programme | Programme name | Client | Project | Project name | Manager | Contract type | Contract value | Cost budget | Actual cost to date | Budget burn | % complete | Burn vs complete | EAC cost | EAC variance | Projected margin | Start | Baseline end | Forecast end | Slip (days) | RAG W38 | RAG W39 | RAG W40
PRG-2001 | Northwind Store Modernisation | Northwind Traders | PRJ-3101 | Project Atlas - POS modernisation | Kavya Iyer | Fixed price + AMS | 4800000 | 3550000 | 3270000 | 92.11% | 78% | 14.11% | 3960000 | 410000 | 17.5% | 2025-03-03 | 2026-12-18 | 2027-03-26 | 98 | Amber | Red | Red
PRG-2001 | Northwind Store Modernisation | Northwind Traders | PRJ-3102 | Managed AMS - store and merchandising apps | Kavya Iyer | Fixed price + AMS | 1450000 | 1060000 | 790000 | 74.53% | 75% | -0.4717% | 1050000 | -10000 | 27.59% | 2024-02-01 | 2027-01-31 | 2027-01-31 | 0 | Green | Green | Green
PRG-2002 | Wingtip Fleet Analytics | Wingtip Logistics | PRJ-3201 | Telematics data platform (Azure Databricks) | Jordan Blake | T&M with outcome bonus | 1600000 | 1090000 | 1040000 | 95.41% | 100% | -4.587% | 1040000 | -50000 | 35% | 2025-06-02 | 2025-11-28 | 2025-11-21 | -7 | Complete | Complete | Complete
PRG-2002 | Wingtip Fleet Analytics | Wingtip Logistics | PRJ-3202 | Predictive maintenance ML - phase 2 | Jordan Blake | T&M with outcome bonus | 850000 | 580000 | 190000 | 32.76% | 31% | 1.759% | 575000 | -5000 | 32.35% | 2026-08-03 | 2027-03-31 | 2027-03-31 | 0 | Green | Green | Green
PRG-2003 | Fabrikam Patient Data Platform | Fabrikam Health | PRJ-3301 | Clinical data ingestion (Epic Clarity to Fabric) | Nikhil Joshi | Fixed price milestones | 1300000 | 910000 | 720000 | 79.12% | 66% | 13.12% | 990000 | 80000 | 23.85% | 2025-09-08 | 2026-10-02 | 2026-11-20 | 49 | Amber | Amber | Amber
PRG-2003 | Fabrikam Patient Data Platform | Fabrikam Health | PRJ-3302 | Quality measures reporting | Nikhil Joshi | Fixed price milestones | 800000 | 560000 | 240000 | 42.86% | 38% | 4.857% | 560000 | 0 | 30% | 2026-03-02 | 2027-02-26 | 2027-02-26 | 0 | Green | Green | Green
PRG-2004 | Woodgrove Data Platform POC | Woodgrove Bank | PRJ-3401 | Lakehouse POC - payments and cards | Lucia Romero | ECIF-funded POC | 240000 | 175000 | 118000 | 67.43% | 72% | -4.571% | 172000 | -3000 | 28.33% | 2026-08-03 | 2026-11-13 | 2026-11-13 | 0 | Green | Green | Green
PRG-2005 | Relecloud AIOps Managed Services | Relecloud | PRJ-3501 | Network operations AIOps run | Omar Siddiqui | Managed service (fixed fee) | 2200000 | 1610000 | 1520000 | 94.41% | 92% | 2.41% | 1640000 | 30000 | 25.45% | 2023-12-01 | 2026-11-30 | 2026-11-30 | 0 | Green | Green | Green
PRG-2006 | Halcyon Claims Data Mart | Halcyon Health | PRJ-3601 | Claims data mart run and enhance | Omar Siddiqui | T&M | 640000 | 430000 | 300000 | 69.77% | 75% | -5.233% | 428000 | -2000 | 33.12% | 2025-04-07 | 2026-12-31 | 2026-12-31 | 0 | Green | Green | Green
PRG-2007 | Wide World Importers WMS Support | Wide World Importers | PRJ-3701 | Warehouse management system AMS | Sam Wright | Managed service (fixed fee) | 1000000 | 760000 | 640000 | 84.21% | 75% | 9.211% | 805000 | 45000 | 19.5% | 2023-01-02 | 2026-12-31 | 2026-12-31 | 0 | Green | Amber | Amber

## Programmes
Programme summary
Strategic programmes tracked by the Delivery Director
Classification: Confidential
Programme | Name | Client | Delivery director | Programme manager | Contract | TCV ($M) | Start | End | Status (W40)
PRG-2001 | Northwind Store Modernisation | Northwind Traders | Arjun Mehta | Kavya Iyer | Fixed price + AMS | 9.7 | 2025-03-03 | 2027-03-26 | Red
PRG-2002 | Wingtip Fleet Analytics | Wingtip Logistics | Arjun Mehta | Jordan Blake | T&M with outcome bonus | 2.6 | 2025-06-02 | 2027-03-31 | Green
PRG-2003 | Fabrikam Patient Data Platform | Fabrikam Health | Arjun Mehta | Nikhil Joshi | Fixed price milestones | 2.1 | 2025-09-08 | 2027-02-26 | Amber
PRG-2004 | Woodgrove Data Platform POC | Woodgrove Bank | Arjun Mehta | Lucia Romero | ECIF-funded POC | 0.24 | 2026-08-03 | 2026-11-13 | Green
PRG-2005 | Relecloud AIOps Managed Services | Relecloud | Arjun Mehta | Omar Siddiqui | Managed service (fixed fee) | 6.6 | 2023-12-01 | 2026-11-30 | Green
PRG-2006 | Halcyon Claims Data Mart | Halcyon Health | Arjun Mehta | Omar Siddiqui | T&M | 1.1 | 2025-04-07 | 2026-12-31 | Green
PRG-2007 | Wide World Importers WMS Support | Wide World Importers | Arjun Mehta | Sam Wright | Managed service (fixed fee) | 3.2 | 2023-01-02 | 2026-12-31 | Amber