Northwind Traders - Quarterly Business Review Q3 2026

Held 17 September 2026, Northwind HQ, Chicago

| Northwind | Lena Fischer (CIO), Daniel Okafor (VP Technology), Mark Ellison (Director, Store Systems), Tanya Brooks (Director, Loyalty & CRM) | Programme | PRG-2001 |
| --- | --- | --- | --- |
| Visionet | Priya Raman, Arjun Mehta, Kavya Iyer, Sam Wright |  |  |

# 1. Delivery review

| Area | Q3 result | Target | Comment |
| --- | --- | --- | --- |
| AMS SLA attainment | 97.8% | 97.5% | Green; 2 P1 incidents, both within SLA |
| Atlas wave 1 checkout time | 77 sec | 80 sec | 18% faster than baseline (94 sec) |
| Atlas wave 2 progress | 196 / 212 stores | 212 by 18 Sep | On track for 18 Sep |
| POS incidents (wave 1 stores) | -22% | -30% | Below target; loyalty lookups are the main cause |

# 2. Client feedback

Lena: AMS team is responsive; Atlas communication to district managers needs to improve.

Mark: two loyalty lookup incidents in August hurt store confidence; wants a permanent fix before peak.

Tanya: loyalty analytics (OPP-24102) is still a priority for 2027, but not before stores are stable.

Daniel said he will be "stepping back from Atlas day to day" over the coming weeks and asked Mark to take more of the programme board. (Note: Daniel left Northwind on 28 Sep.)

# 3. Priorities for Q4 and FY2027

Stable stores through holiday peak (23 Nov - 3 Jan): change freeze from 16 Nov.

Finish wave 3 by the end of Q1 2027 at the latest.

Loyalty personalisation in 2027 (budget request in FY27 plan, not yet approved).

Close 40 underperforming stores by mid-2027: decommission POS and network in those stores.

# 4. Commercial

AMS contract CTR-7020 renews on 1 February 2027. Lena asked for renewal options by mid-November, including a productivity commitment similar to other Visionet AMS clients.

# 5. Actions

| Action | Owner | Due |
| --- | --- | --- |
| Permanent fix for loyalty lookup timeouts | Kavya Iyer | 30 Sep 2026 |
| District manager communication plan for wave 3 | Kavya Iyer | 9 Oct 2026 |
| AMS renewal options paper | Priya Raman | 13 Nov 2026 |
| Store closure decommission plan (40 stores) | Sam Wright | 30 Nov 2026 |