Weekly Status Report - Project Atlas

PRG-2001 Northwind Store Modernisation  |  Week 40: 28 September - 2 October 2026

| Overall status | RED (W39 Red, W38 Amber) | Accountable | Arjun Mehta |
| --- | --- | --- | --- |
| Prepared by | Kavya Iyer | Client | Lena Fischer, Sofia Lindqvist, Mark Ellison |

# Status by dimension

| Dimension | Status | Trend | Comment |
| --- | --- | --- | --- |
| Schedule | Red | Worse | Wave 3 proposed to move from Dec 2026 to 15 Jan - 26 Mar 2027 |
| Budget | Red | Same | Cost burn 92% at 78% complete; EAC raised $410K to $3.96M |
| Scope | Amber | Same | Wave 3 change request (OPP-24103) on hold - CFO spend freeze |
| Quality | Red | Better | INC-48211 resolved; circuit breaker live; de-dup in test |
| Resourcing | Amber | Same | Stabilisation squad of 6 added from AMS bench |
| Client satisfaction | Red | Worse | Formal escalation 29 Sep; CSAT 6.1 in Q3 pulse |

# Highlights this week

Offline fallback configured and tested in all 212 wave 2 stores (30 Sep).

Circuit breaker on loyalty lookup deployed 30 Sep 14:10 CT; load test at 3x Saturday peak passed.

Root cause analysis for INC-48211 sent to Lena Fischer (30 Sep).

Weekly sync on 1 Oct with new VP Technology, Sofia Lindqvist.

# Milestones

| Milestone | Baseline | Forecast | Status |
| --- | --- | --- | --- |
| Wave 2 complete (212 stores) | 18 Sep 2026 | 18 Sep 2026 | Green |
| Loyalty de-duplication in production | 25 Sep 2026 | 13 Oct 2026 | Amber |
| Recovery plan to client | - | 8 Oct 2026 | Amber |
| Wave 3 start (220 stores) | 26 Oct 2026 | 15 Jan 2027 | Red |
| Programme close | 18 Dec 2026 | 26 Mar 2027 | Red |

# Top risks and issues

R-014 Holiday peak instability (score 20) - change freeze from 16 Nov.

I-033 Duplicate loyalty member IDs (~258K) - production fix 13 Oct.

I-034 Sponsor exit - relationship plan with Sofia Lindqvist.

# Decisions needed from Northwind

Agree wave 3 freeze until 15 January 2027 (proposed at 1 Oct sync; Lena agreed in principle).

Nominate a business owner for loyalty data sign-off now that Daniel Okafor has left.