## Slide 1
WEEKLY STATUS | W40 | 28 SEP - 2 OCT 2026
Wingtip Fleet Analytics: on track, pilot depot showing early gains
Visionet | Wingtip Fleet Analytics status, W40 | Fictitious data for testing - Enterprise IQ test corpus
CONFIDENTIAL 1
Green
Overall status
W38 Green, W39 Green
31%
Phase 2 complete
PRJ-3202
33%
Budget burn
$190K of $580K
-23%
Roadside breakdowns
Memphis pilot, 8 weeks
Model v2 retrained on 14 months of telemetry (AUC 0.87)
Memphis pilot depot live since 14 Sep; 41 alerts, 33 confirmed faults
Rotterdam and Hamburg discovery for EU depots (OPP-24171) starts 19 Oct
Next milestone | Date | Status
Depots 2-4 (Nashville, Dallas, Atlanta) | 16 Nov | Green
Maintenance work-order integration (SAP PM) | 4 Dec | Green
Phase 2 complete | 31 Mar 2027 | Green
Notes: Mei Lin asked for a depot manager dashboard by the QBR in January. Carlos Ruiz confirmed SAP PM API access.