Claims Modernisation Programme - Response to RFP CI-2026-014

Prepared for Calder Insurance  |  DRAFT v0.6 for internal review (pricing pending deal desk)

| Client | Calder Insurance (ACC-1014) | Bid owner | Anita Rao, Bid Manager |
| --- | --- | --- | --- |
| RFP reference | CI-2026-014 Claims Modernisation | Solution lead | Ravi Shankar |
| Visionet bid ID | BID-0618 / OPP-24230 | Partners | Guidewire (PartnerConnect Select), AWS |
| Submission due | 20 October 2026, 17:00 ET | Status | Hour 19 of 48 - draft 64% complete |

Draft note Sections 4.2 (solution) and 7 (commercials) are still in draft. Requirement 088 (fixed-price option for phase 1) is open with the deal desk. Do not circulate outside the bid team.

# 1. Executive summary

Calder Insurance wants to replace its 18-year-old mainframe claims platform with Guidewire ClaimCenter on Guidewire Cloud, cut first-notice-of-loss (FNOL) to settlement cycle time by 30%, and retire the Hartford data centre by Q4 2028.

Visionet proposes a three-release programme over 22 months: commercial auto first, then property, then specialty lines. Each release goes live with its own data conversion and a parallel-run window, so Calder never has two claims systems of record for the same line of business.

Proven Guidewire delivery: 2 ClaimCenter implementations and 140 certified Guidewire practitioners, with an accelerator library of 61 pre-built integrations.

Insurance automation built in: our Intelligent Document Processing (IDP) accelerator, live at Litware Insurance, classifies FNOL documents with 94% straight-through accuracy.

Lower migration cost: an AWS migration incentive of up to $120,000 (MAP) has been confirmed for eligibility, funding the data conversion factory.

Hybrid delivery from Hartford: a 9-person on-site core team in Hartford, with build and test from our nearshore centre; see section 6 for the response to requirement 052.

# 2. Our understanding of Calder's objectives

| Calder objective (from RFP section 2) | What it means for the programme | How we respond |
| --- | --- | --- |
| Reduce FNOL-to-settlement cycle time by 30% | Automate intake, triage and straight-through payment for low-complexity auto claims | IDP at FNOL, rules-based triage, ClaimCenter automated payments |
| Retire mainframe claims by Q4 2028 | No more than 2 years of dual running | 3 releases, last go-live in month 22 |
| Improve adjuster productivity | Single desktop, fewer re-keys | ClaimCenter + Guidewire Jutro digital portals |
| Meet NAIC data security model law | Encryption, access logging, vendor oversight | SOC 2 Type II (2026 report), AWS-native controls |
| Predictable cost | Fixed price where scope is stable | Fixed price for release 1 under evaluation (req. 088) |

# 3. Proposed solution

## 3.1 Target architecture

ClaimCenter runs on Guidewire Cloud Platform (AWS us-east-1), integrated with PolicyCenter (Calder retains its current policy admin system until 2029), the Duck Creek billing platform, and Calder's Snowflake claims data warehouse through Guidewire Data Platform.

| Integration | Pattern | Accelerator |
| --- | --- | --- |
| Policy admin (legacy) | Real-time policy lookup via API gateway | GW-INT-014 Policy Adapter |
| FNOL intake (web, call centre, agent) | Event-driven, IDP for attachments | IDP-FNOL v3 |
| Payments (Duck Creek billing) | Batch + API | GW-INT-031 Payments |
| Fraud scoring (FRISS) | Synchronous scoring on claim creation | GW-INT-044 Fraud Hook |
| Data warehouse (Snowflake) | Guidewire Data Platform CDC | GDP-SF Connector |

## 3.2 Release plan

| Release | Scope | Duration | Go-live |
| --- | --- | --- | --- |
| R1 - Commercial auto | FNOL, triage, auto claims, payments, conversion of 41K open claims | 9 months | Aug 2027 |
| R2 - Property | Property claims, catastrophe surge model, vendor portal | 7 months | Mar 2028 |
| R3 - Specialty lines | Specialty and liability, legacy decommission | 6 months | Sep 2028 |

# 4. Delivery approach

We use Guidewire's InsuranceSuite delivery methodology with two-week sprints, a dedicated conversion factory and a joint Calder-Visionet design authority that meets weekly.

## 4.2 Data conversion  [DRAFT - Mei Tanaka to complete]

Conversion follows a staged extract-transform-load with reconciliation at claim, reserve and payment level. We will run four mock conversions before R1 go-live; acceptance requires 100% claim count reconciliation and financial variance below 0.01%.

# 5. Compliance summary

The full compliance matrix (186 requirements) is in Appendix B. Summary as of draft v0.6:

| Status | Requirements | Notes |
| --- | --- | --- |
| Met | 158 | Including 014 ClaimCenter integration and 037 SOC 2 Type II |
| Partial | 13 | Including 052 on-site team in Hartford (hybrid model proposed) |
| Gap | 15 | Including 088 fixed-price option for phase 1 (with deal desk) |

# 6. Team

| Role | Name | Location | Allocation |
| --- | --- | --- | --- |
| Engagement Partner | Marcus Bell | New York | 20% |
| Programme Director | To be confirmed (shortlist: 2) | Hartford | 100% |
| Guidewire Solution Architect | Ravi Shankar | Hartford | 100% (R1) |
| Data Conversion Lead | Mei Tanaka | Remote / Hartford | 100% |
| Delivery team | 11 named people with ClaimCenter experience (8 available from January 2027) | Nearshore | Ramp from month 2 |

# 7. Commercial summary  [DRAFT - awaiting deal desk]

Indicative total programme value: $5.8M over 22 months (time and materials with fixed-price release 1 option under evaluation). Partner incentives (AWS MAP, up to $120,000) are applied after award and are not netted from the price shown.

# 8. Assumptions

Calder provides SMEs for 3 lines of business at 50% allocation during design.

Guidewire Cloud subscription is contracted directly between Calder and Guidewire.

Legacy data extracts are delivered in agreed formats within 10 business days of request.

Calder's Snowflake environment is available for the Guidewire Data Platform connector by month 4.