## Slide 1
V
VISIONET
Crew Operations Platform Modernisation
Orals presentation to Tailspin Airlines evaluation panel
30 September 2026 | Sophie Turner, Anita Rao, Victor Hughes, Ravi Shankar
Visionet | Tailspin Airlines orals, 30 Sep 2026 | Fictitious data for testing - Enterprise IQ test corpus
CONFIDENTIAL 1

## Slide 2
OUR UNDERSTANDING
Summer 2026 showed what the current crew system costs Tailspin
Visionet | Tailspin Airlines orals, 30 Sep 2026 | Fictitious data for testing - Enterprise IQ test corpus
CONFIDENTIAL 2
1,140
Crew-related cancellations
Jun-Aug 2026
$38M
Disruption cost
Tailspin Q2 filing
4.5 hrs
Avg. re-crew time
manual, per disruption
1997
Core system built
COBOL on z/OS
Crew pairing and rostering run on a mainframe batch that cannot re-optimise during irregular operations
Crew schedulers re-key changes across 4 systems; union rules are checked by hand
Tailspin's RFP asks for a cloud-native platform live for the 2027 summer peak (by 1 May 2027)

## Slide 3
OUR SOLUTION
A cloud-native crew platform on AWS, delivered in three increments
Visionet | Tailspin Airlines orals, 30 Sep 2026 | Fictitious data for testing - Enterprise IQ test corpus
CONFIDENTIAL 3
1
Crew data hub
Event stream of roster, flight and crew-qualification changes (Amazon MSK)
2
Recovery optimiser
Re-crews disrupted flights in minutes using union and FAA rule engine
3
Scheduler workbench
One screen for schedulers; replaces 4 legacy green screens
4
Crew mobile app
Trip trades, notifications and acknowledgements
Built on the AWS landing zone we delivered in migration waves 1 and 2 (2025-2026)
Legacy mainframe stays system of record for pay until increment 3

## Slide 4
DELIVERY PLAN
Live for summer 2027, with the mainframe as fallback until pay cuts over
Visionet | Tailspin Airlines orals, 30 Sep 2026 | Fictitious data for testing - Enterprise IQ test corpus
CONFIDENTIAL 4
Increment | Scope | Start | Live | Fallback
1 - Data hub + workbench | Read-only workbench, event hub | Nov 2026 | Feb 2027 | Mainframe primary
2 - Recovery optimiser | Irregular-ops re-crewing, rule engine | Jan 2027 | Apr 2027 | Manual re-crew
3 - Mobile + pay cutover | Crew app, pay interface, decommission | Apr 2027 | Sep 2027 | Parallel pay run
Increment 2 is live 4 weeks before the 1 May 2027 deadline, leaving a buffer for summer readiness testing with crew schedulers.

## Slide 5
PROOF POINTS
Why Visionet: we already run Tailspin's AWS estate
Visionet | Tailspin Airlines orals, 30 Sep 2026 | Fictitious data for testing - Enterprise IQ test corpus
CONFIDENTIAL 5
Chart: Servers migrated to AWS for Tailspin
| Wave 1 (2025) | Wave 2 (2026)
Servers migrated | 412 | 386
Both migration waves delivered on schedule; wave 2 closed 12 June 2026
AWS MAP credits ($210K) lowered Tailspin's migration cost
Crew domain SMEs from 2 airline programmes (references available)
Same AWS account structure and security controls reused: no new landing zone cost

## Slide 6
COMMERCIALS
Commercial summary and next steps
Visionet | Tailspin Airlines orals, 30 Sep 2026 | Fictitious data for testing - Enterprise IQ test corpus
CONFIDENTIAL 6
$2.2M
Total contract value
fixed price per increment
11 months
Duration
Nov 2026 - Sep 2027
23 Oct
Decision
Tailspin evaluation panel
Proposal validity extended to 30 November 2026
Reference calls offered with two airline crew programmes
Optional: AWS MAP modernisation funding to be applied for after award
Notes: Competitors on the shortlist: TCS and Cognizant. Panel asked about union rule engine flexibility - follow up with Elaine Russo with the rules configuration demo by 7 Oct.